## Sheet1
				Status	2024.08.16	Comment	2024.08.22	Comment	2024.08.27	Comment	2024.08.29
Tasks	Start Date	End Data	Responsibility		Risk		Risk
Export CIM data from Lede network	2024.8.7	2024.8.19	Ola/Lede		Medium		High		High	Completed
Define scenario for demonstrator	2024.8.19	2024.8.19	Ola/Phillip		Low	Completed				Completed
Export AMI data for Lede larger area via Event Hub for Upkip	2024.8.15	2024.8.21	Ola/Lede		Low		Medium		High	Completed
Retrieve Historical AMI data for new sensors	2024.8.15	2024.8.21	Kim/Upkip		Low		Medium		High	Completed
Update prediction models on ML for 3000+ AMI meters	2024.8.21	2024.9.2	Roman/Phillip		High		High		High		Medium
Ingest CIM into memgraph	2024.8.19	2024.8.21	Dinesh		Medium		Medium		High	Completed
Export geojson artifacts for Lede	2024.8.21	2024.8.27	Dinesh		Medium		Medium		High		Medium
Export Topology event structure for Lede	2024.8.21	2024.8.27	Dinesh/Phillip		Medium		Medium		High		Medium
Formulate load flow analysis and debug for convergence	2024.8.21	2024.9.6	Phillip		Medium/High		Medium/High		High		High
Implement scenario for demonstrator	2024.9.2	2024.9.9	Phillip		Medium/High		Medium/High		High		High
Generate Geojson Export for visualization frontend	2024.9.2	2024.9.12	Phillip/Bjørn		Low/Medium		Low/Medium		High		Medium